## Final Project - Draft Planning
Title | Status | Milestone | Start date | Due date | Duration
Designated Supervision Session |  |  | 2023-06-01 | 2023-06-01 | 0
Documentation - Alternative Project |  |  | 2023-06-03 | 2023-06-04 | 1
Designated Supervision Session |  |  | 2023-06-06 | 2023-06-06 | 0
Weekly Reflections |  |  | 2023-06-01 | 2023-06-08 | 7
Interview Scheduling - Wireframe | 🏗 In progress | Interview Module | 2023-06-09 | 2023-06-09 | 0
Management of Users Type - Wireframe | 🏗 In progress | Administrative Module | 2023-06-09 | 2023-06-09 | 0
Users Management - Wireframe | 🏗 In progress | Administrative Module | 2023-06-09 | 2023-06-09 | 0
Report of Users - Wireframe | 🏗 In progress | Administrative Module | 2023-06-09 | 2023-06-09 | 0
Management of Interviewees - Participants of the Interview - Wireframe | 🏗 In progress | Interview Module | 2023-06-10 | 2023-06-10 | 0
Audio Transcription - Wireframe | 🏗 In progress | Interview Module | 2023-06-10 | 2023-06-10 | 0
Management of Interview Audio Records - Wireframe | 🏗 In progress | Interview Module | 2023-06-10 | 2023-06-10 | 0
Logoff Area- Sign In - Sign Up - Wireframe | 🏗 In progress | Information Security | 2023-06-10 | 2023-06-10 | 0
Management of Calendar - Appointment Confirmation - Wireframe | 🏗 In progress | Interview Module | 2023-06-10 | 2023-06-10 | 0
Report - Interview Scheduling - Wireframe | 🏗 In progress | Interview Module | 2023-06-11 | 2023-06-11 | 0
Draft Plan | 🏗 In progress | Overall Documentation | 2023-06-07 | 2023-06-11 | 4
Starting Code Repository - Coding | 🆕 New | Code Engineering | 2023-06-11 | 2023-06-12 | 1
Designated Supervision Session |  |  | 2023-06-15 | 2023-06-15 | 0
Weekly Reflections |  |  | 2023-06-12 | 2023-06-15 | 3
Admin - Management of Users Type - Coding | 🆕 New | Administrative Module | 2023-06-13 | 2023-06-16 | 3
Draft Chapter 1 |  |  | 2023-06-12 | 2023-06-18 | 6
Interview Module - Authentication Mode - Coding | 🆕 New | Interview Module | 2023-06-21 | 2023-06-21 | 0
Weekly Reflections |  |  | 2023-06-19 | 2023-06-22 | 3
Designated Supervision Session |  |  | 2023-06-22 | 2023-06-22 | 0
Planning | 🏗 In progress |  | 2023-06-07 | 2023-06-22 | 15
Admin - Users Management - Coding | 🆕 New | Administrative Module | 2023-06-21 | 2023-06-27 | 6
Weekly Reflections |  |  | 2023-06-26 | 2023-06-29 | 3
Designated Supervision Session |  |  | 2023-06-29 | 2023-06-29 | 0
Interview Module - Logoff Area Sign In and Sign Up - Coding | 🆕 New | Information Security | 2023-06-26 | 2023-06-30 | 4
Admin - Report of Users - Coding | 🆕 New | Administrative Module | 2023-06-28 | 2023-07-02 | 4
Designated Supervision Session |  |  | 2023-07-06 | 2023-07-06 | 0
Weekly Reflections |  |  | 2023-07-03 | 2023-07-06 | 3
Interim Project Presentation |  |  | 2023-07-03 | 2023-07-10 | 7
Weekly Reflections |  |  | 2023-07-10 | 2023-07-13 | 3
Interview Module - Management of Interviewees - Coding | 🆕 New | Interview Module | 2023-07-11 | 2023-07-14 | 3
Interview Module - Interview Scheduling - Coding | 🆕 New | Interview Module | 2023-07-15 | 2023-07-18 | 3
Weekly Reflections |  |  | 2023-07-17 | 2023-07-20 | 3
Designated Supervision Session |  |  | 2023-07-20 | 2023-07-20 | 0
Interview Module - Calendar Management - Appointment Confirmation - Coding | 🆕 New | Interview Module | 2023-07-19 | 2023-07-22 | 3
Interview Module - Management of Audio - Coding | 🆕 New | Interview Module | 2023-07-23 | 2023-07-27 | 4
Weekly Reflections |  |  | 2023-07-24 | 2023-07-27 | 3
Designated Supervision Session |  |  | 2023-07-27 | 2023-07-27 | 0
Weekly Reflections |  |  | 2023-07-31 | 2023-08-03 | 3
Interview Module - Audio Transcription - Coding | 🆕 New | Interview Module | 2023-07-28 | 2023-08-03 | 6
Designated Supervision Session |  |  | 2023-08-10 | 2023-08-10 | 0
Documentation - Project Report (PDF) |  |  | 2023-08-01 | 2023-08-12 | 11
Demo Recording / Screencast |  |  | 2023-08-01 | 2023-08-13 | 12
Final Reflection |  |  | 2023-08-10 | 2023-08-14 | 4

## Gantt Chart11062023
45078